Reviewing Blocker Bugs:

(The following would be inserted after the second paragraph under the above section title I know we don't use indented paragraph numbering, it's an old long established habit. The advantage is that subordination is visually clear.)

1. Exceptions for Last Minute Proposed Blocker Bugs
  1. The team must agree according to the two prior paragraphs in this section, that a Last Minute Proposed Blocker Bug has the character of a Blocker Bug before being process per this section.
  2. A Last Minute Blocker Bug shall be evaluated for being delayed to the next release cycle according to the criteria below. A Last Minute Proposed Blocker Bug that meets any of the listed criteria may be delayed to the next release cycle as a Blocker Bug if the team agrees. Other Last Minute Proposed Blocker Bugs must be corrected before the current cycle Final Release.
    1. Any bug that can not be fixed in a reasonable amount of time considering the current Release Cycle or due to complexity or resource constraints.
    2. Any bug in non-vital system operation or release package installed application operation.

1. Delaying the current Release:
  1. Delaying the current release cycle must take into account all of the following criteria.
    1. Consider if the cause of the delay should have been caught earlier in the current cycle. What changes in process could help moving such discoveries earlier in the cycle?
    2. Adding the current proposed delay to any prior delays, is the total delay becoming unacceptable in regard to Fedora release policy?
    3. Will the current proposed delay enable other desirable work to be completed for the release?
    4. Impact on down stream projects.